## Sheet1
Test Name | Test Procedure | Criteria for Success | Completed | Notes
Power rails. | Plug the three main PCBs together. Hook up power supply set to 3.7V to VBATT and turn on main power switch. Measure the power rails. | 1V, 2V, and 3V3 rails all are close to their expected value. +-11V rails should be off. Current consumption looks ok (<100 mA). ON LED turns on.
LiPo | Disconnect power supply, connect LiPo instead. Measure the power rails again. | Voltages are as expected from the previous test.
USB Charging | Connect USB-C to PCB to charge the LiPo. | Voltage rails should turn off. Charge LED should turn on (orange). Voltage of battery slowly increases. When charging is done, charge LED turns white.
ESP32 Basic Test | Connect ESP32 and run Blink. | ESP32 blinks the ON LED.
DAC Test | Run ADC_DAC_test on ESP32. Run for every channel of the DAC. | Measured DAC voltages (VGSRAW and VDSRAW) are consistent with what is reported in serial.
ADC Test | Using a breadboard, connect a potentiometer and resistor between the 2V reference rail and GND to create a resistor divider. Feed the output of the resistor divider into VMEAS. Run ADC_DAC_test. | Vary VMEAS by turning the potentiometer around. Probe VMEAS, it should be close to what the ADC is reporting.
DAC and ADC test | Feed the ouput of one of the DAC channels into VMEAS. Run ADC_DAC_test for every channel. | ADC's reported voltage is consistent with what is being written to the DAC.
Gate Voltage Power Rails | Run gate_voltage_test. Test the +-11V power rails. | The +-11V power rails are now on.
Gate Voltage Test, x1 | Run gate_voltage_test with x1 amplification. | Gate voltages measured from a multimeter are consistent with what the gate_voltage_test is reporting in serial.
Gate Voltage Test, x10 | Run gate_voltage_test with x10 amplification. | Gate voltages measured from a multimeter are consistent with what the gate_voltage_test is reporting in serial.
Gate Switch Test | Flip the global gate switch while running gate_voltage_test. | All gate voltages turn off.
Transimpedance Amplifier Test | Solder wires to VDS_BUFF and IDS. Connect these wires to a breadboard with a resistor (>= 1k) in between. Run transimpedance_test, updating test_resistor with whatever resistance was used. | Current expected and current measured are about the same.
Drain Demultiplexer Test | Run multiplexer_test. Test the drain demultiplexer at addresses 0 and 31, measure voltage at VDS1 and VDS32. | With code set to address 0, Vds voltage is observed at VDS1. With code set to address 31, Vds voltage is observed at VDS32.
Source Multiplexer Test | Run multiplexer_test. Test the source multiplexer by choosing addresses 0 and 31 and supplying either IDS1 or IDS31 with an analog voltage (like from a resistor divider). | ADC voltage reported changes as voltage of the chosen mux input changes (not that ADC voltage will not be equal to the mux input voltage)
Demux+Mux Test | Run multiplexer_test.ino. Solder wires to drain 31 and source 31, connect these to a breadboard with a test resistor (>= 1k) in between. (Basically the Transimpedance test but now with the multiplexers in between). | Current expected and current measured are about the same.
Final Test | Run final_boss. Try out Vds sweeps, Vgs sweeps, Vgs amplifcations, etc all at once. | Vgs voltages are what we expect them to be, current readings from transimpedance amplifer are accurate, power rails are stable.
Test Name | Test Procedure | Criteria for Success | Completed | Notes
Boost converter | Hook up boost converter to main PCB assembly. Test heater voltage output. | Before the heater is turned on, the output should be 0V. When heater is turned on, the output is about 7V. Heater ON LED turns on.
Heater | Connect heater to boost converter. Check temperature. (WARNING: Heater gets very hot!) | Heater should rise to about 100C within a few minutes.
Temp Check | Attach thermistor to the side of the heater, and connect the thermistor to the ESP32 Carrier PCB (HEAT THERM header) | ESP32 serial reports correct thermistor readings.
Test Name | Test Procedure | Criteria for Success | Completed | Notes
Humidity Sensor | Connect BME680 to main PCB assembly. Run BME680_test. | Serial reports reasonable temp readings and humidity readings. When you breathe on the sensor, the humidity and temperature should rise.